## Executive Summary
AEGIS ASSURANCE — EXECUTIVE SUMMARY (18 Jul 2026, executed self-review)
Item | Finding | Reference | Where
Scope | Aegis v4.9 kernel — dual-harness trading system in /aegis, AQE engine untouched at repo root
Epics / User stories / Tasks | 11 / 35 / 60+ | Taxonomy: PM journey × functional capability | ASSURANCE_REVIEW.md §1
Components built | 21 skills · 9 tools · 4 calculators · 6 contracts · 2 packagers · 1 MCP server · 7 governance docs | § Architecture sheet | aegis/
Verification battery (EXECUTED today) | 15 PASS / 15 — zero failures | § Verification Log sheet | 2026-07-18T09:23:47
Live connector proof | Tiger (account summary) + FMP (SPY quote) answered from session | PASS | 18 Jul
Feed integrity | Tripwires PASS on the LIVE 18-Jul export (177 rows) | PASS | 18 Jul
GitHub state | Commit staged on main in local clone + bundle fallback; push completes via PM-1 action box | OPEN — PM-1 | DEPLOY.md
Open items | 7 backlog entries (BL-001..008 minus shipped BL-007), schema-valid, in the development pipeline | § Gaps sheet | data/persistent/backlog.jsonl
Rulings | D-1..D-11 + D-7a, each with what it retires | § decisions_log.md | charter/
Verdict | BUILT & INTERNALLY VERIFIED. Live-fire pending: PM actions (PM-1..PM-4) → glue items → shadow week → acceptance checklist → first armed session last. |  | DEPLOY.md §C

## Requirements Trace
REQUIREMENTS TRACEABILITY — PM requirement → epic → component → location → status
Req | PM requirement (source ruling) | Epic | Story/Task | Component | Repo location | Status | Verification / next
R-01 | Remove cognitive load; one plan by 16:00, approve by 21:00 | E4 | US-4.1/4.2 | premarket skill + plan contract | aegis/skills/premarket · contracts/plan.schema.json | ✅ built | first live run pending
R-02 | True agentic: voices work independently before consensus | E3 | US-3.1..3.5 | 10 isolated voice skills + shared engine + nomination contract | aegis/skills/voice-* | ✅ built | swarm live-run pending
R-03 | Voices speak from their own literature | E3 | US-3.1 | canon sections (9–13 principles each) pinned in cards | aegis/skills/voice-*/SKILL.md | ✅ built | PM can read/correct text
R-04 | Detect lens = 10th nominator (D-5) | E3 | US-3.2 | detect_lens card, lens/radar fields only | aegis/skills/voice-detect_lens | ✅ built | ledger will judge the seat
R-05 | Event filter on nominated names only, pre-deliberation (D-11) | E3 | US-2.3→E3 | premarket step 7 reorder | aegis/skills/premarket | ✅ rewired today | —
R-06 | Universe = daily open screen (D-3) | E2 | US-2.1 | universe_screen.py (FMP) | aegis/tools/universe_screen.py | 🟡 built | needs FMP key live run (PM-4)
R-07 | Feed trusted blindly | E2 | US-2.2 | schema (generated from live feed) + tripwires | aegis/contracts + tools/tripwires.py | ✅ EXECUTED | PASS on live export
R-08 | One order-capable agent only | E5 | US-5.1 | staging-gatekeeper, 7 checks; orchestrators stripped | aegis/skills/staging-gatekeeper | ✅ built | refusal test in acceptance list
R-09 | PM autonomy switch: /arm default-preview, fixed 05:30 expiry (D-7/D-7a) | E5 | US-5.2 | autopilot.py + caps in parameters | aegis/tools/autopilot.py | ✅ EXECUTED | arm→disarm cycle tested
R-10 | Real-money mechanics: two-step sizing, post-fill $50 check | E5 | US-5.3 | sizing.py | aegis/tools/calculators/sizing.py | ✅ EXECUTED | CLOV example computed
R-11 | Code watches, agents wake | E6 | US-6.1 | market_hours skill + existing alert engine | aegis/skills/market_hours · src/alerts | ✅ built | loader glue = BL-003
R-12 | Daily journal from broker truth | E7 | US-7.1 | post_market skill + journal contract | aegis/skills/post_market · contracts/journal.schema.json | ✅ built | first reconcile at deploy
R-13 | Hedge check in held-book step (PM 18 Jul) | E4 | T-4.5.1 | premarket step 4 wiring + hedge_engine.py | aegis/skills/premarket · tools/calculators/ | ✅ shipped (BL-007) | —
R-14 | Four data shelves + flat growth | E8 | US-8.1/8.3 | data tree + janitor + rollups | aegis/data · tools/janitor.py | ✅ built | —
R-15 | Legacy journal mess cleaned once | E8 | US-8.2 | migrate_legacy.py + manifest | aegis/tools/migrate_legacy.py | ⬜ OPEN | BL-002: run on PC
R-16 | Outcome memory per voice | E8 | US-8.4 | nomination_ledger.py (record/track/report) | aegis/tools/nomination_ledger.py | 🟡 built | price feed = BL-004
R-17 | PM config layer: 1-line tweaks, auto-logged (no spaghetti) | E1 | US-1.3 | set_param (validate/refuse/log/commit) | aegis/tools/set_param.py | ✅ EXECUTED | self-test in battery
R-18 | Learning & managed change (D-8) | E9 | US-9.3 | development skill + backlog contract (retirement mandatory) | aegis/skills/development · contracts/backlog.schema.json | ✅ built | 8 items already flowing
R-19 | Evidence before votes (BULLISH_BOS lesson) | E9 | US-9.4 | measure_proposal.py w/ volatility control | aegis/tools/measure_proposal.py | ✅ built | —
R-20 | Dual-harness deployability | E10 | US-10.1/10.2 | 2 packagers + DEPLOY.md 3 paths + acceptance checklist | aegis/packaging · DEPLOY.md | ✅ EXECUTED | both builds ran today
R-21 | Local-hybrid, fail-safe, private GitHub archive (D-9) | E10 | US-10.4 | topology + PM action box + env template | CONTEXT Part 7 · DEPLOY.md | ✅ documented | PM-1/PM-2 self-serve
R-22 | Weekly stepping-back view + CS Weekly | E11 | US-11.1 | weekly skill + drop folder (sample present) | aegis/skills/weekly · data/persistent/cs_weekly | ✅ built | —

## User Journey
USER JOURNEY — stage × PM action × system behaviour × skills × commands × artifacts
Stage | SGT | PM does | System does | Skills engaged | Commands | Artifacts out
Sunday | — | Read weekly report | Weekly: CS Weekly ingest → posture → WTD/MTD/YTD + system perf → churn → rule review | weekly | /weekly | weekly report, posture memory
Premarket build | 13:00–16:00 | — | Universe screen → AQE fetch+tripwires → held+hedge check → 10 isolated nominations → tally → EVENT FILTER (nominated only, D-11) → macro/SRM weather → deliberation → plan assembly | premarket + 10 voices + gatekeeper(requests) | /pm | sod/: universe, nominations×10, committee, plan DRAFT
Approve | 16:00–21:00 | /plan → /approve (or except) → optionally /arm; stage pre-authorised brackets | Plan approval token written; triggers → alert universe | staging-gatekeeper (previews) | /plan /approve /arm /ap | plan APPROVED + previews + autopilot state
Sleep (US market) | 21:30–04:00 | sleep | Alert engine polls → trigger fires → MH orchestrator wakes → gatekeeper 7 checks → preview (or armed Tiger confirm within caps) → post-fill protocol | market_hours + staging-gatekeeper | /watch /killed (morning) | intraday/: fires, previews/refusals, fills, post-fill
Wake — accounting | 04:00–10:00 | — | Journal (broker truth, dynCap, SL audit) → metrics → completeness audit → GitHub archive commit → janitor | post_market + auditor | /close (manual rerun) | eod/: journal, metrics, audit
Wake — learning | after post-market | Read 10:00 summary; tap backlog approvals | Scorer (miss taxonomy) → learning agent → backlog items (retirement mandatory) → dev pipeline | performance_scorer + learning_agent + development | /review /backlog | review report, backlog.jsonl updates

## Architecture
ARCHITECTURE COMPONENTS — plane × type × inputs × outputs × location
Component | Plane | Type | Inputs | Outputs | Auth/keys | Location
AQE engine | Data plane | pre-existing | bars, universe panels | aqe_daily_export.json + alerts | — | src/ (repo root)
universe_screen.py | Data plane | tool | FMP screener+bars | universe_DATE.json | FMP key | aegis/tools
tripwires.py | Data plane | assurance tool | export + journal | BLOCK/clean verdict | — | aegis/tools
calculators (sizing, bs_price, hedge, alpaca) | Data plane | tools | plan/chain inputs | sizes, prices, hedge candidates | Alpaca embedded keys | aegis/tools/calculators
nomination_ledger.py / janitor / migrate_legacy / measure_proposal / set_param / autopilot | Data plane | utility tools | shelves, panel, params | ledger, rollups, archives, param commits, autopilot state | — | aegis/tools
5 process orchestrators | Control plane | orchestration skills | all above via catalog | 5 daily artifacts | — | aegis/skills/{premarket,market_hours,post_market,weekly,design_review}
Staging Gatekeeper | Control plane (boundary) | the ONLY order-capable agent | requests + plan + autopilot state | previews / refusals / confirms(armed) / post-fill | Tiger connector | aegis/skills/staging-gatekeeper
10 voices + common engine | Judgment plane | isolated subagents | universe + own data menu + own ledger memory | nomination.json ×10 | — | aegis/skills/voice-*
Deliberation session | Judgment plane | committee | deliberation set + weather | committee.json w/ dissent | — | premarket steps 8–9
Assurance trio + development | Judgment/Control | skills | eod artifacts + ledger | audit, review, backlog | — | aegis/skills/{auditor,performance_scorer,learning_agent,development}
Packagers | Build | generators | kernel | Claude plugin + Kimi pack (dist/, never hand-edited) | — | aegis/packaging
Connectivity | Access | MCP/REST | — | Tiger connector (live-proven) · FMP (live-proven) · Alpaca REST · IBKR MCP (built, untested) | per endpoints.json/.env | aegis/tools/mcp + account connectors

## Data Map
DATA & EXECUTION DATA LAYER — artifact × shelf × producer × consumers × contract × retention
Artifact | Shelf/location | Producer | Consumers | Contract | Retention
universe_DATE.json | sod/DATE | universe_screen.py | all 10 voices | criteria embedded | 30d raw → rollup+zip
aqe_daily_export.json | output/ → sod/DATE | AQE engine (08:30) | premarket, voices (menus), gatekeeper (brackets) | aqe_export.schema + tripwires | engine-owned + shelf copy
nominations ×10 | sod/DATE/nominations | voice skills | tally, event filter, ledger | nomination.schema | 30d
committee_DATE.json | sod/DATE | deliberation | gatekeeper check-1, plan | committee artifact | 30d
plan_DATE.json + approval | sod/DATE | premarket + PM | gatekeeper check-6, market-hours, alert loader | plan.schema | 30d
staging previews/refusals | intraday/DATE/staging | GATEKEEPER ONLY | PM, auditor | preview spec | 30d
fills + post-fill records | intraday/DATE | gatekeeper post-fill | journal merge | — | 30d
autopilot state + log | persistent/ | /arm /disarm | gatekeeper (every confirm) | in tool | append forever
aegis_journal_DATE.json | eod/DATE | post_market | next-day AQE held, weekly, /fa | journal.schema | 30d raw; rollup forever
metrics + audit + review | eod/DATE | post_market + D&R | morning summary, scorer | — | 30d
ledger.jsonl | persistent/ | nomination_ledger.py | scorer, voices (own memory) | ledger.schema | rows close @15d
backlog.jsonl | persistent/ | development pipeline | PM (morning), coding agent | backlog.schema | forever (dev memory)
rollups + monthly zips + legacy archive | persistent/rollups + archive/ | janitor / migration | humans | manifest.csv | forever
GitHub daily archive commit | repo (private) | post_market step | disaster recovery | git history | forever

## Orchestration Map
ORCHESTRATION — standing vs triggered × process × skills invoked × outputs × gates
Mode | Trigger/clock | Process | Steps | Invokes | Outputs | Gates enforced
STANDING | Sun (scheduler) | Weekly | 5 steps | — | weekly report + posture | —
STANDING | 13:00 SGT | Premarket | 11 steps | voices×10, gatekeeper(requests), SRM/hedge inside step 4 | plan DRAFT by 16:00 | staleness, tripwires, event filter (post-nomination)
TRIGGERED | PM /approve ≤21:00 | Approval | — | gatekeeper (previews) | plan APPROVED, alerts loaded | approval token required downstream
TRIGGERED | PM /arm | Autopilot arm | — | autopilot.py | armed state (expires 05:30) | only PM can arm
TRIGGERED | alert fire 21:30–04:00 | Market-hours wake | 6 steps | gatekeeper (7 checks → preview/confirm) | fire log, staging records | caps, kill-conditions disarm-first
STANDING | 04:05 SGT | Post-market | 4 steps + archive commit + janitor | auditor | journal, metrics, audit | journal must schema-validate
STANDING | after post-market | Design & Review | 5 steps | scorer, learning, development(capture) | review, backlog items | retirement mandatory
STANDING | 10:00 SGT | Morning summary push | assembler (BL-005 glue) | — | one push | —
TRIGGERED | PM /param X Y | Config change | set_param | — | param commit + log entry | type/key validation, refuse new keys
TRIGGERED | finding approved | Development | 6-stage pipeline | coding agent, shadow run | branch → shipped version | 2 failed shadows = auto-reject

## Verification Log
EXECUTED VERIFICATION BATTERY — 2026-07-18T09:23:47 — 15/15 PASS
Test | Method | Result | Detail
All python compiles (kernel) | py_compile on every .py | PASS | 15 files
Rulebook YAML valid | yaml.safe_load | PASS | ['meta', 'capital', 'risk', 'universe', 'committee', 'brackets', 'orders', 'regime', 'srm'
Parameters YAML valid | yaml.safe_load | PASS | ['meta', 'capital', 'risk', 'regime', 'universe', 'committee', 'schedule', 'retention', 'a
6 contracts valid JSON Schema | json.load each | PASS | ['AQE Daily Export', 'Backlog Item', 'Aegis Journal (PTJ successor)', 'Nomination Ledger E
Tripwires vs LIVE 18-Jul export | subprocess run | PASS | tripwires clean: 177 rows
Autopilot arm→status→disarm cycle | subprocess x3 | PASS | armed->05:30 expiry->disarmed
set_param no-op validate+log+revert path | subprocess | PASS | OK retention.raw_days: 30 -> 30 (logged + committed if repo)
Claude adapter builds | build_claude.py | PASS | built /home/claude/aegis/dist/claude-plugin/aegis-v4
Kimi adapter builds (21 skills) | build_kimi.py | PASS | built /home/claude/aegis/dist/claude-plugin/aegis-v4 built /home/claude/aegis/dist/kimi
Backlog items schema-valid | jsonschema validate | PASS | 8 items
Sizing worked example (CLOV) | sizing.size() | PASS | {'shares': 3401, 'shares_r': 3401, 'shares_volcap': 7307, 'capped_by': 'r', 'risk_usd': 10
Git commit staged on main (local clone) | git log | PASS | 2e2b851 aegis kernel v4.9 — portable dual-harness kernel in single /aegis folder (charter,
Tiger MCPv7 connector live | get_account_summary via session connector | PASS | account 50179929, NAV 55687.69 (18 Jul)
FMP connector live | quote-short SPY via session connector | PASS | SPY 743.29 (18 Jul)
AQE repo cloned & mapped | git clone + tree inspect | PASS | src/{engines,analyzer,alerts,intraday,scanner...} run_daily.bat output/

## Gaps & Backlog
OPEN ITEMS — all schema-valid in data/persistent/backlog.jsonl, flowing through the development pipeline
ID | Item | Plan | Blocked on | Priority
BL-001 | Push kernel to repo | Commit staged on main locally + bundle; PM-1 action box finishes it | PM-1 | HIGH — everything else flows from repo
BL-002 | Run legacy journal migration | Script built+compiled; run on PC against Drive folder | PM presence | MED
BL-003 | Alert-universe loader (plan → src/alerts config) | Glue script, ~50 lines | none | HIGH for live
BL-004 | Ledger price-feed job (FMP → prices.json) | Small scheduled script | PM-4 (.env) | MED
BL-005 | Morning-summary assembler (10:00 push) | Stitches eod artifacts into one push | none | MED
BL-006 | Task Scheduler entries | Generated on /schedule after PM-2 confirm | PM-2 | HIGH for autonomy
BL-008 | Shadow week → acceptance checklist → first armed session LAST | One supervised week; daily parity diffs | all above | GATE for real money